## Instructions
C5IMP Risk, Issue, and Opportunity Register
CVN C5I Modernization Program (C5IMP) - DRAFT TEMPLATE - NOT OFFICIAL POLICY - UNCLASSIFIED. Placeholder data only.
Purpose
Consolidated register of program risks (future uncertain events), issues (realized problems), and opportunities, with mitigation plans and a 5x5 scoring matrix. Reviewed at every OIPT and CCB.
How to Use This Workbook
- Write risks as 'If <condition>, then <consequence>' statements.
- Score Likelihood and Consequence 1-5; Risk Score is calculated as L x C and Risk Level derives from the Risk Matrix tab bands (1-6 Low, 8-12 Moderate, 15-25 High).
- Promote a risk to the Issues tab when it is realized; retain the risk row and cross-reference the Issue ID.
- Every High risk requires an active row on Mitigation Plans with funded actions and an owner.
Maintenance Rules
- The SharePoint copy of this workbook is authoritative. Edit in the browser; do not download/re-upload working copies.
- Update within 2 business days of any governance event per the C5IMP Governance SOP.
- Use dropdown values only in controlled columns; do not overwrite data validation or table formatting.
- Do not delete rows with history; mark items Complete or Cancelled instead.
- Do not enter classified information; use approved placeholders and references.

## Lookups (hidden)
StatusList | PriorityList | RiskLevelList | HullList | SystemCategoryList | OrgList | DecisionStatusList | DocTypeList | AvailTypeList | RatingList | YesNoList | RACIList | ScoreList
Not Started | Critical | High | CVN-XX | C2 Suite | TYCOM N6 | Submitted | Charter | PIA | Green | Yes | R | 1
In Progress | High | Moderate | CVN-YY | Communications | TYCOM N43 | In Evaluation | SOP | DPIA | Yellow | No | A | 2
On Hold | Medium | Low | CVN-ZZ | Networks | TYCOM N4 | Pending Decision | Form | CIA | Red |  | C | 3
Blocked | Low |  | Class-Wide | Combat Systems I/F | NAVSEA | Approved | Memorandum | Emergent Window | Gray |  | I | 4
Pending Decision |  |  |  | ISR | PEO Carriers | Approved w/ Conditions | Assessment |  |  |  | R/A | 5
Complete |  |  |  | Navigation | PEO C4I/PMW | Disapproved | Plan
Cancelled |  |  |  | Cyber Infrastructure | Ship's Force | Deferred | Minutes
[5 empty] | RMC |  | Decision Record
[5 empty] | Shipyard |  | AAR
[5 empty] | Program Office |  | Guide
[5 empty] | Fleet Staff |  | Tracker

## Risks
Risk ID | Risk Statement (If/Then) | Hull | System Category | Likelihood (1-5) | Consequence (1-5) | Risk Score | Risk Level | Owner Org | Mitigation Ref | Review Date | Status
RSK-2026-001 | [If GFE terminal delivery slips, then CVN-XX PIA install window is missed] | CVN-XX | Communications | 4 | 4 |  | High | PEO C4I/PMW | MIT-001 | 2026-06-20 | In Progress
RSK-2026-002 | [If cableway survey reveals interference, then backbone routing requires redesign] | CVN-YY | Networks | 3 | 3 |  | Moderate | NAVSEA | MIT-002 | 2026-07-01 | In Progress
RSK-2026-003 | [If crew training quotas are unavailable, then turnover is delayed] | CVN-XX | Communications | 2 | 3 |  | Low | TYCOM N6 |  | 2026-08-01 | Not Started

## Issues
Issue ID | Issue Statement | Source Risk ID | Hull | System Category | Priority | Owner Org | Resolution Plan | Need Date | Status
ISS-2026-001 | [Shipyard crane availability conflict during antenna removal window] |  | CVN-XX | Communications | High | RMC | [Re-sequence with shipyard scheduler] | 2026-06-25 | In Progress

## Opportunities
Opp ID | Opportunity Statement | Hull | System Category | Potential Benefit | Owner Org | Pursue? | Plan | Status
OPP-2026-001 | [Combine ISR and C2 display refresh into one install team visit] | CVN-ZZ | ISR | [Reduced ship disruption; cost avoidance placeholder] | Program Office | Yes | [Joint work package study] | In Progress

## Mitigation Plans
Mitigation ID | Risk ID | Mitigation Action | Owner Org | Due Date | Status | Residual Likelihood | Residual Consequence | Notes
MIT-001 | RSK-2026-001 | [Weekly delivery telecon with vendor; identify alternate install window] | PEO C4I/PMW | 2026-06-30 | In Progress | 2 | 4 | [Placeholder]
MIT-002 | RSK-2026-002 | [Early ship check of cableway route] | NAVSEA | 2026-07-15 | Not Started | 2 | 3 | [Placeholder]

## Risk Matrix
C5IMP 5x5 Risk Matrix (Score = Likelihood x Consequence)
Consequence ->
|  | 1 | 2 | 3 | 4 | 5
| Likelihood 5 | 5 | 10 | 15 | 20 | 25
| Likelihood 4 | 4 | 8 | 12 | 16 | 20
| Likelihood 3 | 3 | 6 | 9 | 12 | 15
| Likelihood 2 | 2 | 4 | 6 | 8 | 10
| Likelihood 1 | 1 | 2 | 3 | 4 | 5
Bands: 1-6 Low (green), 8-12 Moderate (yellow), 15-25 High (red). Tailor bands per program direction.