## Instructions
C5IMP Availability Integration Tracker
CVN C5I Modernization Program (C5IMP) - DRAFT TEMPLATE - NOT OFFICIAL POLICY - UNCLASSIFIED. Placeholder data only.
Purpose
Tracks integration of C5I modernization work into CVN availabilities: events, work packages, ship access needs, test milestones, dependencies, and turnover items.
How to Use This Workbook
- One row per availability on Availability Events; all other tabs key to the Availability ID.
- Work Packages maps each modernization item to its availability work package with install windows.
- Log compartment/aloft/service access needs on Ship Access Requirements before the integration lock milestone.
- Testing Milestones must cover every installed item; turnover discrepancies go to Turnover Items with owners and due dates.
Maintenance Rules
- The SharePoint copy of this workbook is authoritative. Edit in the browser; do not download/re-upload working copies.
- Update within 2 business days of any governance event per the C5IMP Governance SOP.
- Use dropdown values only in controlled columns; do not overwrite data validation or table formatting.
- Do not delete rows with history; mark items Complete or Cancelled instead.
- Do not enter classified information; use approved placeholders and references.

## Lookups (hidden)
StatusList | PriorityList | RiskLevelList | HullList | SystemCategoryList | OrgList | DecisionStatusList | DocTypeList | AvailTypeList | RatingList | YesNoList | RACIList | ScoreList
Not Started | Critical | High | CVN-XX | C2 Suite | TYCOM N6 | Submitted | Charter | PIA | Green | Yes | R | 1
In Progress | High | Moderate | CVN-YY | Communications | TYCOM N43 | In Evaluation | SOP | DPIA | Yellow | No | A | 2
On Hold | Medium | Low | CVN-ZZ | Networks | TYCOM N4 | Pending Decision | Form | CIA | Red |  | C | 3
Blocked | Low |  | Class-Wide | Combat Systems I/F | NAVSEA | Approved | Memorandum | Emergent Window | Gray |  | I | 4
Pending Decision |  |  |  | ISR | PEO Carriers | Approved w/ Conditions | Assessment |  |  |  | R/A | 5
Complete |  |  |  | Navigation | PEO C4I/PMW | Disapproved | Plan
Cancelled |  |  |  | Cyber Infrastructure | Ship's Force | Deferred | Minutes
[5 empty] | RMC |  | Decision Record
[5 empty] | Shipyard |  | AAR
[5 empty] | Program Office |  | Guide
[5 empty] | Fleet Staff |  | Tracker

## Availability Events
Availability ID | Hull | Availability Type | Fiscal Year | Start Date | End Date | Phase | C5IMP Integration Lead | Status | Notes
AV-2026-01 | CVN-XX | PIA | FY2X | 2026-07-01 | 2026-12-15 | Execution | [Name] | In Progress | [Placeholder]
AV-2027-01 | CVN-YY | DPIA | FY2X | 2026-12-01 | 2027-08-30 | Planning | [Name] | In Progress | [Placeholder]

## Work Packages
Work Package ID | Availability ID | Item ID | Title | Executing Org | Install Start | Install Complete | Status | Critical Path? | Notes
[WP-1234] | AV-2026-01 | C5IMP-MOD-2026-001 | [Comms suite upgrade] | RMC | 2026-07-15 | 2026-08-15 | In Progress | Yes | [Placeholder]
[WP-2345] | AV-2027-01 | C5IMP-MOD-2026-002 | [Backbone refresh incr 1] | Shipyard | 2026-12-15 | 2027-02-15 | Pending Decision | No | [Awaiting CCB]

## Ship Access Requirements
Req ID | Availability ID | Work Package ID | Space/Compartment (Placeholder) | Access Type | Window Needed | Conflicts With | Coordinated With Shipyard? | Status
ACC-001 | AV-2026-01 | [WP-1234] | [Comm center placeholder] | [Rip-out + install] | 2026-07-15 to 2026-08-15 | [Concurrent vent work] | Yes | In Progress
ACC-002 | AV-2026-01 | [WP-1234] | [Mast/antenna platform] | [Aloft work + crane] | 2026-07-20 to 2026-07-30 | [Radar silence windows] | No | Blocked

## Testing Milestones
Milestone ID | Availability ID | Item ID | Test Event (Placeholder) | Planned Date | Actual Date | Result | Status | Discrepancies -> Turnover ID | Notes
TST-001 | AV-2026-01 | C5IMP-MOD-2026-001 | [SOVT placeholder - terminal group] | 2026-09-01 |  |  | Not Started |  | [Placeholder]

## Dependencies
Dependency ID | Availability ID | Predecessor | Successor | Type | Need Date | Status | Blocked? | Notes
DEP-001 | AV-2026-01 | [Cableway rip-out WP-1230] | [WP-1234 install] | Finish-to-Start | 2026-07-14 | In Progress | No | [Placeholder]

## Turnover Items
Turnover ID | Availability ID | Item ID | Description | Owner Org | Due Date | Status | Accepted by Ship? | Notes
TO-001 | AV-2026-01 | C5IMP-MOD-2026-001 | [Outstanding label plate corrections] | RMC | 2026-12-01 | Not Started | No | [Placeholder]