## Instructions
C5IMP SharePoint Content Inventory and Metadata Plan
CVN C5I Modernization Program (C5IMP) - DRAFT TEMPLATE - NOT OFFICIAL POLICY - UNCLASSIFIED. Placeholder data only.
Purpose
Build specification for the C5IMP SharePoint site: every library, list, metadata column, view, permission group, web part, and page mapping the site owners must create. Used during Phases 1-6 of the Implementation Roadmap and audited monthly thereafter.
How to Use This Workbook
- Build the site to match these tabs exactly; record any approved deviation in the Notes column.
- Create site columns from Metadata Columns first, then bind them to libraries/lists per Document Libraries and Lists tabs.
- Create views per the Views tab before adding web parts.
- Permissions Groups defines group composition and access level; the Restricted Decision Records Group uses unique permissions.
- Web Parts and Page Mapping mirror the Web Part Employment Matrix in 04_SharePoint_Architecture.
Maintenance Rules
- The SharePoint copy of this workbook is authoritative. Edit in the browser; do not download/re-upload working copies.
- Update within 2 business days of any governance event per the C5IMP Governance SOP.
- Use dropdown values only in controlled columns; do not overwrite data validation or table formatting.
- Do not delete rows with history; mark items Complete or Cancelled instead.
- Do not enter classified information; use approved placeholders and references.

## Lookups (hidden)
StatusList | PriorityList | RiskLevelList | HullList | SystemCategoryList | OrgList | DecisionStatusList | DocTypeList | AvailTypeList | RatingList | YesNoList | RACIList | ScoreList
Not Started | Critical | High | CVN-XX | C2 Suite | TYCOM N6 | Submitted | Charter | PIA | Green | Yes | R | 1
In Progress | High | Moderate | CVN-YY | Communications | TYCOM N43 | In Evaluation | SOP | DPIA | Yellow | No | A | 2
On Hold | Medium | Low | CVN-ZZ | Networks | TYCOM N4 | Pending Decision | Form | CIA | Red |  | C | 3
Blocked | Low |  | Class-Wide | Combat Systems I/F | NAVSEA | Approved | Memorandum | Emergent Window | Gray |  | I | 4
Pending Decision |  |  |  | ISR | PEO Carriers | Approved w/ Conditions | Assessment |  |  |  | R/A | 5
Complete |  |  |  | Navigation | PEO C4I/PMW | Disapproved | Plan
Cancelled |  |  |  | Cyber Infrastructure | Ship's Force | Deferred | Minutes
[5 empty] | RMC |  | Decision Record
[5 empty] | Shipyard |  | AAR
[5 empty] | Program Office |  | Guide
[5 empty] | Fleet Staff |  | Tracker

## Document Libraries
Library | Purpose | Content Types | Required Metadata | Versioning | Approval Required? | Build Status | Notes
Program Documents | Controlled charters, SOPs, plans | Charter; SOP; Plan | Document Type; Status; Owner; Review Date | Major (check-out required) | Yes | Not Started
Templates | Blank templates only | All template types | Document Type; Last Updated | Major | Yes | Not Started | [Read-only for most users]
Modernization Trackers | Authoritative Excel trackers | Tracker | Document Type; Owner; Last Updated | Major+minor | No | Not Started | [Edit in browser only]
Configuration Baseline | Baseline register + references | Tracker; Plan | Hull; System Category; Status; Owner | Major (check-out required) | Yes | Not Started | [CM staff edit only]
Decision Records | Completed decision records | Decision Record | Hull; System Category; Decision Authority; Status | Major | Yes | Not Started | [Restricted group]
Meeting Records | Agendas, read-aheads, minutes | Minutes | Meeting Series; Hull; Status | Major | No | Not Started
Lessons Learned | After Action Reports | AAR | Hull; Availability; System Category | Major | No | Not Started

## Lists
List | Purpose | Key Columns | Source of Truth For | Build Status | Notes
Intake List | Modernization intake submissions | Title; Sponsor Org; Hull; System Category; Priority; Status | Intake pipeline | Not Started | [Pairs with intake form template]
Action Items List | Mirror of action tracker for web part views | Action; Owner Org; Due Date; Status; Priority | Action dashboards | Not Started | [Sync from workbook or use list as master - choose one]
Risk List | Top risks surfaced on dashboard | Risk; Hull; Risk Level; Owner Org; Review Date | Dashboard risk view | Not Started
Stakeholder Directory | POC roster | Name; Org; Role; Email; SharePoint Group | People web parts | Not Started
Battle Rhythm Calendar | Events calendar | Event; Series; Date; Location | Events web parts | Not Started

## Metadata Columns
Column | Type | Values/Source | Required On | Notes
Hull | Choice | CVN-XX; CVN-YY; CVN-ZZ; Class-Wide | Most libraries/lists | [Extend per fleet]
System Category | Choice | C2 Suite; Communications; Networks; Combat Systems I/F; ISR; Navigation; Cyber Infrastructure | Most libraries/lists
Program Office | Choice | TYCOM; NAVSEA; PEO Carriers; PEO C4I/PMW; Other | Program Documents; Decision Records
Document Type | Choice | Charter; SOP; Form; Memorandum; Assessment; Plan; Minutes; Decision Record; AAR; Guide; Tracker | All libraries
Status | Choice | Draft; In Review; Approved; Superseded | All libraries | [Document status, not item status]
Decision Authority | Choice | ESB; CCB; WIPT; Expedited | Decision Records
Availability | Choice | [PIA FY2X; DPIA FY2X; CIA FY2X+1; N/A] | Trackers; AARs
Fiscal Year | Choice | [FY2X; FY2X+1; FY2X+2] | Trackers
Handling Caveat | Choice | [Placeholder caveat values per command guidance] | All libraries | [Classification/handling placeholder - tailor before use]
Owner | Person | Site directory | All libraries
Review Date | Date | - | Program Documents
Last Updated | Date (auto) | Modified | All | [Use built-in Modified where possible]
CCB Required | Yes/No | - | Intake List
Readiness Impact | Choice | High; Moderate; Low; None | Intake List; Risk List

## Views
Library/List | View Name | Filter/Sort | Audience | Used On Page | Build Status
Intake List | Triage Queue | Status=Submitted, sort by date | Action officers | Intake and Change Review | Not Started
Intake List | My Submissions | Created By = [Me] | Sponsors | Intake and Change Review | Not Started
Action Items List | Overdue | Due<today AND Status<>Complete | All | Risks/Issues/Actions; Dashboard | Not Started
Action Items List | By Organization | Group by Owner Org | Leads | Risks/Issues/Actions | Not Started
Risk List | High Risks | Risk Level=High | Leadership | Dashboard | Not Started
Decision Records | Pending Decisions | Status=Pending | CCB members | Decisions and CCB | Not Started
Meeting Records | By Series | Group by Meeting Series | All | Governance and Meetings | Not Started
Program Documents | By Hull | Group by Hull | All | Multiple | Not Started

## Permissions Groups
Group | Access Level | Membership (Placeholder) | Build Status | Scope Notes
Site Owners | Full Control | [2-3 named site owners] | Not Started | Structure, permissions, views
TYCOM Editors | Edit | [TYCOM N6/N43/N4 staff] | Not Started | All except Decision Records edit
NAVSEA Editors | Edit | [NAVSEA modernization staff] | Not Started | All except Decision Records edit
PEO/PMW Contributors | Contribute | [PEO/PMW reps] | Not Started | Trackers, intake, meeting records
Ship Viewers | Read | [Ship's Force C5I] | Not Started | Read all unrestricted content
Shipyard/RMC Contributors | Contribute (scoped) | [RMC/shipyard planners] | Not Started | Availability content only
Read-Only Leadership | Read | [Flag/SES staff] | Not Started | All unrestricted content
Restricted Decision Records Group | Edit (unique perms) | [CCB secretariat + chair] | Not Started | Decision Records library only

## Web Parts
Web Part | Primary Use | Configuration Notes
Hero | Major navigation on Home | [5-tile layout to top pages]
Quick Links | Key workflows and templates | [Button layout; link to intake, trackers, templates]
Document Library | Controlled document access | [Point at specific view, not whole library]
List | Actions, risks, decisions | [Use filtered views; enable inline edit only for contributors]
Highlighted Content | Recently updated / high priority | [Filter by metadata: Priority=High or Modified last 14 days]
News | Modernization updates | [Post from Home; audience targeting optional]
Events | Battle rhythm and CCB events | [Bind to Battle Rhythm Calendar list]
People | Key POCs | [Bind to Stakeholder Directory entries]
Text | Process guidance blocks | [Short guidance only; link to documents for detail]
Embed / Power BI | Future dashboard integration | [Placeholder pending tenant approval]
Forms placeholder | Intake workflow | [If tenant policy allows; else use list new-item form]

## Page Mapping
Page | Purpose | Web Parts | Sources | Build Status
Home | Orientation and navigation | Hero; News; Events; Quick Links; People | News; Battle Rhythm Calendar; Stakeholder Directory | Not Started
Modernization Dashboard | Status rollup | Highlighted Content; List (risks, actions); Embed placeholder | Trackers; Risk List; Action Items List | Not Started
Intake and Change Review | Intake pipeline | Quick Links; List (Intake views); Text | Intake List; Templates | Not Started
Configuration Baseline | Baseline visibility | Document Library; Text | Configuration Baseline library | Not Started
Availability Integration | Availability work | Document Library; List; Events | Trackers; Battle Rhythm Calendar | Not Started
Risks / Issues / Actions | Burn-down | List x3 (views); Highlighted Content | Risk List; Action Items List | Not Started
Governance and Meetings | Battle rhythm | Events; Document Library; Quick Links | Meeting Records; Calendar | Not Started
Decisions and CCB | Decision traceability | List (Decision log views); Document Library | Decision Records | Not Started
Readiness Assessments | Readiness visibility | Document Library; Highlighted Content | Readiness workbook + reports | Not Started
References and Templates | Self-service | Document Library (Templates view); Quick Links; Text | Templates library | Not Started
Lessons Learned | Knowledge capture | Document Library; Highlighted Content | Lessons Learned library | Not Started