AIRCRAFT CARRIER C5I MODERNIZATION PROGRAM (C5IMP)

# C5IMP SharePoint Implementation Roadmap

Phased Build, Pilot, and Fleet Expansion Plan

| Document Control Field | Entry |
| --- | --- |
| Document Number | C5IMP-RDMP-001 |
| Version | 0.1 (DRAFT) |
| Effective Date | [DD MMM YYYY] |
| Prepared By | [Action Officer Name / Code] |
| Reviewed By | [Branch Head / Code] |
| Approved By | [Approval Authority / Code] |
| Next Review Date | [DD MMM YYYY] |
| Classification | UNCLASSIFIED (template) - [Insert handling caveat placeholder] |
| SharePoint Location | [C5IMP Site / Library / Folder] |

DRAFT TEMPLATE - NOT OFFICIAL POLICY - UNCLASSIFIED
DISTRIBUTION STATEMENT PLACEHOLDER - Insert appropriate distribution statement prior to release.

# Revision History

| Version | Date | Author / Code | Description of Change | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | [DD MMM YYYY] | [Name / Code] | Initial draft template. | [Name / Code] |

# 1. Purpose

This roadmap sequences the build-out of the C5IMP SharePoint administrative tool suite from site shell through fleet-level adoption.

# 2. Phases

| Phase | Scope | Exit Criteria | Owner | Target (Placeholder) |
| --- | --- | --- | --- | --- |
| 1. Build site shell | Site, pages, navigation, permission groups created | All 11 pages exist; groups populated | Site Owners | [Week 1-2] |
| 2. Create libraries/lists | All libraries and lists from the Content Inventory created | Inventory tab matches site | Site Owners | [Week 2-3] |
| 3. Apply metadata | Site columns and content types applied | Required columns enforced on all libraries | Site Owners | [Week 3-4] |
| 4. Upload templates | Word/Excel suite uploaded to Templates and Tracker libraries | All files present with metadata | Action Officer Lead | [Week 4] |
| 5. Configure views | Standard views (By Hull, Overdue, Pending Decision, etc.) built | Views verified by user reps | Site Owners | [Week 5] |
| 6. Add web parts | Pages assembled per Web Part Employment Matrix | Page-by-page checklist complete | Site Owners | [Week 5-6] |
| 7. Pilot | One hull or one availability run end-to-end on the site | Pilot AAR complete; punch list dispositioned | Program Office Lead | [Week 7-18] |
| 8. Refine governance | SOP/CCB Charter updates from pilot lessons | Updated documents approved | Program Office Lead | [Week 18-20] |
| 9. Expand to fleet-level use | Remaining hulls onboarded; training delivered | All hulls reporting via site | TYCOM N6 / NAVSEA Leads | [Week 20+] |

# 3. Pilot Recommendation

Pilot with a single CVN availability ([CVN-XX] [PIA FYxx placeholder]) entering its planning window: run intake, triage, CCB, availability integration, and one readiness assessment cycle entirely on the site before fleet expansion.

# 4. Risks to Implementation

Tenant policy may restrict Forms or Power BI web parts - confirm early (mitigation: list-based intake and Excel rollups).

Tracker adoption may lag if email habits persist - mitigation: chairs refuse non-SharePoint read-aheads after Phase 6.

Metadata discipline erodes without enforcement - mitigation: required columns plus monthly content audit by site owners.

# Approval

| Role / Organization | Name | Signature | Date |
| --- | --- | --- | --- |
| Program Office Lead | [Name] |  | [DD MMM YYYY] |
| TYCOM N6 Representative | [Name] |  | [DD MMM YYYY] |
| Site Owner | [Name] |  | [DD MMM YYYY] |